# APPLICATION

This document applies to all shipboard personnel.

# PURPOSE

The purpose of this document is to provide instructions for dry-dock and repair periods.

# RESPONSIBILITIES

# Master and Chief Engineer -

  - Coordinate with Office to finalise dry dock specification in E48 & E49 and Technical Defect List (E24.

  - Ensure vessel is prepared and ready for dry docking.

  - Coordinate with officers and crew in dock to follow up on daily tasks status.

  - Ensure proper recording and reporting of work done is carried out.

  - Assist the Vessel Manager in monitoring, inspection and acceptance of work being done.

  - Raise requisitions as instructed by the Vessel Manager.

  - Attend daily meetings with the shipyard.

  - Ensure all work carried out is in accordance with proper safety standards and at no times the safety of vessel or crew is compromised.

Warning:

The Vessel Manager, Master and Chief Engineer are jointly responsible for ensuring that tasks, Dry Dock Tasks, are closely monitored, supervised and verified to be correctly completed on a daily basis. Lapses in completion of any of these items (which need to be carried out when the vessel is in dry-dock), pose severe hazard to safety and environment. Also, carrying out repairs on these items when the vessel is in service, can be very difficult and costly. Maintain records of completion and verification by Vessel Manager, Chief Engineer and Master, both on board the vessel and ashore.

# GENERAL

Note:

The Vessel Manager is the only person that may authorise work during drydocking and repair periods.

Caution:

Unscheduled jobs in the yard must be avoided.

# PREPARATION PRIOR TO ARRIVAL AT SHIPYARD

# Arrival conditions

    - Shipyard requires vessel to have specific max aft draft max trim. This condition can be achieved by adjusting ballast water.

    - Ascertain from loadicator that strength and stability conditions can be met for the draft conditions as required for docking.

    - De-ballast to meet arrival draft conditions.

# Gas freeing

    - Ensure vessel is gas free for docking, prior arrival ship yard.

    - Open manholes and ventilate all cargo tanks and water ballast tanks, empty fuel oil tanks and void spaces.

    - Arrange safety handrails and hazard tape cordoning in way of all open manholes.

# Cleaning of hull and tank spaces

    - Clean all hull spaces, such as cargo tanks, cargo holds, water ballast tanks and bilges before arrival at the shipyard.

    - Coordinate with Vessel Manager and discuss the plan.

    - Send daily updates of cleaning progress to the Vessel Manager.

# Protection of accommodation spaces and items

    - Cover floors of alleyways, mess rooms, smoke rooms, offices and chairs with plastic.

# Work plan for deck, engine and electrical

Send the DD work plan to be done by ship staff to Vessel manager.

Note:

Ship staff should give emphasis to carrying out non routine work that can only be done in dry- docking or which need stoppage or blackout.

# Shipside valves and sea water pipelines needing renewal:

    - Identify and tag all overboard valves which need to be overhauled, and sea water pipelines requiring renewal.

    - Appoint one person in-charge for liaising with yard ship repair manager for carrying out the job.

# Deck department jobs

    - Cargo holds / tanks de-mucking / washing / cleaning and hold bilges cleaning and drying.

    - Any loose items which can be stolen (example brass items like fire hydrant nozzles etc.) must be secured well before arrival.

    - All manhole / entrance doors of enclosed spaces (including ballast tanks, pipe tunnel, stool spaces) open and close by ship staff. Manhole doors de-rusted and painted before boxing up with new gaskets.

    - Performance test like bilge suction test of Bosun store, chain lockers, and water ingress alarms.

    - Measure brake lining of windlass and mooring winches. Order required lining well in advance, in order to have it on board before vessel arrival dry dock.

    - Check performance of deck machinery (windlass and mooring winches). Identify and request for any repair requirements (hydraulic, mechanical and electrical components), well in advance.

    - Check the condition of hatch cover packing and booby hatch cover packing. Order any required packings well in advance, in order to have these onboard before vessel’s arrival dry dock.

    - Check the condition of all air vent pipe floats including FO tanks and order spares for any damaged floats well in advance in order to have it onboard before vessel arrival dry dock.

    - Check the condition of hatch cover drain channel non return valves and order spares for any damaged non return valves well in advance in order to have it onboard before vessel arrival dry dock.

    - Identify the requirement for any other structural or cargo system repairs, and co-ordinate with Vessel Manager for getting these affected.

    - Prepare ship’s office or one of the common spaces (mess rooms) to be used as meeting room with shipyard personnel. Cover all chairs and floor in identified meeting area and alleyways.

# Immediately upon arrival dry dock / shipyard:

    - To continue de-ballasting and pump out remaining water.

    - To lower anchor chains.

    - WBT bottom plug to show to shipyard.

    - All repair jobs to be shown to shipyard repair team without delays.

    - Remove material from lifeboat immediately on arrival and restore before departure from shipyard.

# DURING DRY DOCKING

The following items shall be considered as guidance only. Please refer to the docking specification as prepared by the Vessel Manager.

  - Class surveys

  - Support specialist engineer, dockyard and class surveyor during dry-docking repair.

  - Regular fire patrol, specifically of hot work area and other areas where repair work is ongoing, during stay in yard.

  - Survey item: ballast water and fuel oil tanks’ vent heads open, inspect and box up.

  - Newly repaired steel area to paint as and when get chance.

  - Lifeboat wire renewal.

  - Mud in ballast tanks cleared for bell mouth inspection and for surveyor’s inspection.

  - Survey items like FW tanks, distilled water tank cleaning.

  - Leaky fire hydrant valves if any to overhaul.

  - Empty paint cans inventory to monitor.

  - Mud removed from chain locker, ballast tanks to monitor and record.

  - Final inspection and testing of repair job by shipyard, specialist engineer.

  - De-rusting / painting of super structure.

  - De-rusting / painting of fwd mast, aft / radar mast, funnel, deck houses, provision crane, navigations lights.

  - Checking of all ballast tanks - Carry out internal structural repairs, zinc anode renewals, as required.

  - Continue deck maintenance / deck upgrade

  - Checking of mooring winches & windlass brake lining.

  - Inspection and calibration of equipment requiring shore servicing – example multi-gas detectors and other gas measuring instrument, UTI tapes, temperature and pressure calibration equipment & master gauges etc.

  - Ensure all cargo and ballast valve operation is tested and no leaks from hydraulic lines inside tanks.

Caution:

MARPOL compliance for bilge, sludge, food waste & sewage disposal must at all times must be done with yard & local port guidelines

# PLANNING AND PRIORITIES AFTER DRY DOCKING

# Speed and consumption

    - Monitor speed and consumption on regular basis to compare performance before and after dry-docking

Caution:

Ensure accurate recording of fuel consumption.

    - Record main engine performance during sea trial after docking or at first available opportunity, in fair weather and send to Vessel Manager at the earliest

    - Report fresh water production in 24hrs

# Seaworthiness

    - Confirm all booby hatch covers and ventilators butterfly nuts and installed back and all covers are tightened and are sealing properly.

    - All cleats are in position and tightness adjusted wherever needed

    - Close all ballast tank and fuel tank air vents which were opened up for maintenance

    - All ballast tank manhole covers checked for tightness

    - Water ingress alarm system should be retested well before arrival port to reconfirm all is working well

Note:

Most likely cause would be some common component trouble such as wiring discontinuity etc.

# Cargo worthiness

    - Please ensure all debris and dust is removed from cargo holds / tanks, void spaces and hatch covers underside

    - Seals and gaskets of covers to check and confirm in good condition

# LSA / FFA

    - All LSA and FFA should be tested in presence of Chief Engineer and Master particular attention to given to lifeboat engines starting and batteries, emergency generator load test and batteries, emergency fire pump starting from local and remote

    - Pump should develop pressure immediately and not by trial and error

    - All equipment should be confirmed to have returned in its original location as per approved LSA / FFA plan

    - All equipment that were removed and kept in locker prior arriving dry-dock must be returned to respective locations

    - Prepare for PSC Inspections

Note:

Third officer needs to be supervised by Chief Officer / Master for PSC preparations.

# Upgrading and housekeeping:

    - All hatch cover top sides and deck needs to be washed thoroughly with fire hose first and then using high pressure fresh washer.

    - All stores / spares / pipes should be kept indoors. Highest standards of accommodation cleanliness and hygiene must be restored.

    - Engine room also needs cleaning of tank top and cleaning painting for improving appearance of engine room.

    - No flexible hoses and wilden pumps should be left lying in different locations and should be kept under lock & key in dedicated locker and usage log should be maintained.

    - All overboard valves and associated pipelines tag seals to be refitted.

# MACHINERY SURVEYS AND REPORTING

Note:

Chief Engineers may undertake certain surveys if approved by Class Society to do so.

  - When a survey is done by a Chief Engineer, it must be recorded in the engine room log book and a detailed report must be made

  - The report shall contain details of any dismantling work undertaken, calibration and measurement of clearances, list of spares renewed, re-assembly and testing procedures and results as applicable

  - As far as possible, the report shall also include photographs

  - The original report shall be presented to the Class Surveyor and a copy shall be forwarded to the Vessel Manager

  - Any particular item or items to be opened may be scheduled for survey once the surveyor from the Classification Society is present

  - The Master survey listing shall be updated and a E61- Hull & Machinery Survey report shall be submitted to the Vessel Manager( TSI)

  - Report maintenance done in the Planned Maintenance System

  - Continuous Machinery Surveys (CMS) records must be updated

# REFERENCED FORMS AND CHECKLISTS

E61- Survey Report for Hull & machinery.